## Sheet1
ID | Story | Estimation (hours) | Priority (1-3) | Sprint When Finished
1 | Load .set files for ErrP visualization | 4 | 1 | 1
2 | Display averaged ErrP waveforms as time series plots | 6 | 1 | 1
3 | Implement file loading interface | 6 | 1 | 1
4 | Select specific time window | 2 | 1 | 1
5 | Select specific EEG channels from dropdown | 2 | 1 | 1
6 | Build visualization tool without MNE dependency | 10 | 1 | 1
7 | Display topographic maps showing spatial distribution of brain activity | 4 | 2 | 1
8 | Display time series + topo map joint plot | 4 | 2 | 1
9 | Clear and replace loaded files | 2 | 2 | 1
10 | Organize code into modular structure | 2 | 2 | 1
11 | Add event markers and response indicators to visualizations | 3 | 1 | 1
12 | Fix epoch times to autocorrect if out of bounds | 2 | 2 | 2
13 | Tabbed view for multiple files | 2 | 1 | 2
14 | Save graph button | 2 | 3 | 2
15 | Package application as standalone executable with PyInstaller | 6 | 1 | 2
16 | UI updates | 6 | 2 | 2
17 | Fix topo map for fewer sensors | 2 | 1 | 2
18 | Research ganglion data repo | 2 | 1 | 2
19 | Parsing .set file better for cyber security and check magic numbers on csv files | 3 | 1 | 2
20 | Change live mode button to open flanker task/eeg generator | 2 | 3 | 2
21 | Select multiple channels (checkbox) | 2 | 1 | 2
22 | Adding flag that allows to pass into file path to auto load instead of browse (for testing purposes) | 3 | 2 | 2
23 | Convert csv to .set | 4 | 1 | 2
24 | Pressing 'enter' now lets user reload | 2 | 2 | 2
25 | Create a log system so unless we run it with the system in a debug mode we do not output info to terminal | 4 | 2 | 2
26 | Get app running in cloud | 7 | 1 | 2
27 | Icon for application | 4 | 3
28 | Event dropdown (highlight/show different event epochs/time occured ?) | 5 | 1
29 | Updating help dialog to either be our ReadMe or update ReadMe to reflect the help dialog | 3 | 2
30 | Detect ErrPs in real-time during task execution | 8 | 1
31 | Integrate with PsyToolkit flanker task | 10 | 1
32 | Handle continuous (non-epoched) EEG data | 12 | 1
33 | Implement tools for ErrP detection | 10 | 1
34 | Documentation per function (input, output, functionality)
35 | Update ReadMe
36 | Update help button to parse readme on github so if readme is updated the help is updated
37 | Code cleanup
38 | Test with OpenBCI Ganglion
39 | Project site update with documentation
40 | Unit tests |  | 3
41 | Add final executable to repo
42 | Icon once pyinstaller is working
43 | Add flag info to ReadMe
44 | User guide doc
45 | Development guide doc (how to modify)
46 | Install/Deployment guide doc
47 | Test plan/cases doc
48 | FAQs/Gotchas doc